## README
Pilot Control Center – collection data
Simulated sample data: Atlanta, GA site, 8 production days (W3 Mon – W4 Fri) plus bookings for W5 Mon. Snapshot as of 2026-10-26 08:00.
How to use
1. Import this workbook into Google Sheets (File → Import → Upload → Replace spreadsheet).
2. Each day, the on-site lead adds Sessions rows and updates the gold columns (results, upload, client QC). Recruitment updates Participants.
3. Download as .xlsx (File → Download → Microsoft Excel) and use "Load data" on the Command center tab to refresh the dashboard.
Tabs
Participants – one row per recruit: ContributorID, site, demographics (ancestry, gender, age band, height), status.
Sessions – one row per booked visit: station, lighting, supervisor, device, task results, upload and client QC status.
Plan – daily targets from the schedule engine (default inputs); used for plan vs actual.
Devices – the 6 client prototype devices and their status.
Quotas – demographic recruitment targets (ancestry, gender, age band, height band).
Height is measured at check-in (sets the device stand); Height band: <160 cm · 160–175 cm · >175 cm.
Settings – values the dashboard reads (as-of date, target, utilization floor, makeup plan).
Allowed values
Session type: Session 1 · Session 2 · Makeup ¦ Showed up, Upload confirmed, Client QC sampled, Client QC reviewed: Y · N (blank = not yet)
Client QC spot-checks a 25% sample. Client QC sampled = Y marks the sessions the client picked; Client QC reviewed and result apply only to those.
Selfie task / Device task (supervisor sign-off, first attempt): Pass · Fail. A Fail retaken on the spot is noted in Notes.
Client QC result: Pass · Fail, filled when Client QC reviewed = Y. Unsampled sessions are accepted on supervisor sign-off one business day after capture.
A Contribution is validated once 2 sessions on distinct days are accepted (unsampled and settled, or sampled and passed).
Participant status: Booked · Active · Complete · Dropped · Withdrew before start
Gold header = columns the team edits daily. Session ID format: SES-YYMMDD-<station><slot>. All names and IDs are fictional.

## Participants
Participant ID | Site | Ancestry group | Gender | Age band | Height (cm) | Height band | Recruit date | First session date | Status | Contribution validated date
CTR-536794 | Atlanta, GA | Hispanic / Latino | Female | 55+ | 168 | 160–175 cm | 2026-10-03 | 2026-10-12 | Complete | 2026-10-16
CTR-876409 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 177 | >175 cm | 2026-10-02 | 2026-10-12 | Complete | 2026-10-20
CTR-620149 | Atlanta, GA | Hispanic / Latino | Male | 18–34 | 174 | 160–175 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-19
CTR-249673 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 171 | 160–175 cm | 2026-10-03 | 2026-10-12 | Complete | 2026-10-16
CTR-899832 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 172 | 160–175 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-16
CTR-443006 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 173 | 160–175 cm | 2026-10-08 | 2026-10-12 | Complete | 2026-10-15
CTR-773171 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 160 | 160–175 cm | 2026-10-09 | 2026-10-12 | Complete | 2026-10-19
CTR-480215 | Atlanta, GA | European (Eastern, Western) | Male | 55+ | 164 | 160–175 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-16
CTR-691441 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 174 | 160–175 cm | 2026-10-09 | 2026-10-12 | Dropped
CTR-590976 | Atlanta, GA | European (Eastern, Western) | Female | 18–34 | 171 | 160–175 cm | 2026-10-09 | 2026-10-12 | Complete | 2026-10-16
CTR-873116 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 188 | >175 cm | 2026-10-03 | 2026-10-12 | Complete | 2026-10-19
CTR-770027 | Atlanta, GA | Black / African American / Caribbean | Male | 55+ | 176 | >175 cm | 2026-10-04 | 2026-10-12 | Complete | 2026-10-16
CTR-889917 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 179 | >175 cm | 2026-10-07 | 2026-10-12 | Dropped
CTR-489966 | Atlanta, GA | Hispanic / Latino | Female | 18–34 | 167 | 160–175 cm | 2026-10-02 | 2026-10-12 | Complete | 2026-10-16
CTR-764637 | Atlanta, GA | Middle Eastern / North African | Female | 35–54 | 151 | <160 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-605004 | Atlanta, GA | European (Eastern, Western) | Male | 55+ | 162 | 160–175 cm | 2026-10-08 | 2026-10-12 | Complete | 2026-10-16
CTR-682433 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 153 | <160 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-222413 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 175 | 160–175 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-360020 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 153 | <160 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-139974 | Atlanta, GA | Hispanic / Latino | Male | 18–34 | 162 | 160–175 cm | 2026-10-09 | 2026-10-12 | Complete | 2026-10-16
CTR-479835 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 162 | 160–175 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-15
CTR-401194 | Atlanta, GA | Hispanic / Latino | Female | 55+ | 161 | 160–175 cm | 2026-10-05 | 2026-10-12 | Complete | 2026-10-16
CTR-357954 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 167 | 160–175 cm | 2026-10-09 | 2026-10-12 | Complete | 2026-10-16
CTR-581574 | Atlanta, GA | Middle Eastern / North African | Female | 55+ | 163 | 160–175 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-16
CTR-858494 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 170 | 160–175 cm | 2026-10-08 | 2026-10-12 | Complete | 2026-10-19
CTR-731921 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 179 | >175 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-493627 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 167 | 160–175 cm | 2026-10-05 | 2026-10-12 | Complete | 2026-10-15
CTR-997935 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 184 | >175 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-19
CTR-844268 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 170 | 160–175 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-16
CTR-316031 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 165 | 160–175 cm | 2026-10-02 | 2026-10-12 | Complete | 2026-10-16
CTR-537205 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 174 | 160–175 cm | 2026-10-03 | 2026-10-12 | Complete | 2026-10-19
CTR-889146 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 191 | >175 cm | 2026-10-04 | 2026-10-12 | Complete | 2026-10-19
CTR-531995 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 182 | >175 cm | 2026-10-09 | 2026-10-12 | Complete | 2026-10-19
CTR-183971 | Atlanta, GA | Middle Eastern / North African | Female | 18–34 | 167 | 160–175 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-746884 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 162 | 160–175 cm | 2026-10-04 | 2026-10-12 | Complete | 2026-10-19
CTR-570285 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 195 | >175 cm | 2026-10-08 | 2026-10-12 | Complete | 2026-10-19
CTR-990459 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 178 | >175 cm | 2026-10-06 | 2026-10-12 | Complete | 2026-10-16
CTR-660542 | Atlanta, GA | Black / African American / Caribbean | Female | 18–34 | 151 | <160 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-16
CTR-852337 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 160 | 160–175 cm | 2026-10-04 | 2026-10-12 | Complete | 2026-10-19
CTR-321217 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 160 | 160–175 cm | 2026-10-08 | 2026-10-14 | Complete | 2026-10-21
CTR-976324 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 162 | 160–175 cm | 2026-10-03 | 2026-10-12 | Complete | 2026-10-19
CTR-790282 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 162 | 160–175 cm | 2026-10-04 | 2026-10-12 | Complete | 2026-10-19
CTR-415425 | Atlanta, GA | European (Eastern, Western) | Female | 18–34 | 161 | 160–175 cm | 2026-10-05 | 2026-10-12 | Complete | 2026-10-20
CTR-942159 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 174 | 160–175 cm | 2026-10-09 | 2026-10-12 | Complete | 2026-10-15
CTR-927040 | Atlanta, GA | Hispanic / Latino | Female | 18–34 | 154 | <160 cm | 2026-10-07 | 2026-10-12 | Complete | 2026-10-19
CTR-122934 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 180 | >175 cm | 2026-10-05 | 2026-10-14 | Complete | 2026-10-19
CTR-710363 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 155 | <160 cm | 2026-10-05 | 2026-10-14 | Complete | 2026-10-20
CTR-942442 | Atlanta, GA | Hispanic / Latino | Male | 18–34 | 173 | 160–175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-20
CTR-420748 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 176 | >175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-19
CTR-993230 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 172 | 160–175 cm | 2026-10-09 | 2026-10-14 | Dropped
CTR-661915 | Atlanta, GA | Black / African American / Caribbean | Male | 55+ | 174 | 160–175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-20
CTR-434783 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 179 | >175 cm | 2026-10-04 | 2026-10-14 | Complete | 2026-10-19
CTR-283977 | Atlanta, GA | Middle Eastern / North African | Male | 55+ | 185 | >175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-19
CTR-396867 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 183 | >175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-19
CTR-436935 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 174 | 160–175 cm | 2026-10-09 | 2026-10-14 | Complete | 2026-10-20
CTR-762193 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 167 | 160–175 cm | 2026-10-05 | 2026-10-14 | Complete | 2026-10-19
CTR-697809 | Atlanta, GA | Middle Eastern / North African | Male | 55+ | 181 | >175 cm | 2026-10-11 | 2026-10-14 | Complete | 2026-10-19
CTR-476209 | Atlanta, GA | Black / African American / Caribbean | Female | 18–34 | 152 | <160 cm | 2026-10-08 | 2026-10-16 | Dropped
CTR-787855 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 173 | 160–175 cm | 2026-10-08 | 2026-10-14 | Complete | 2026-10-20
CTR-215875 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 160 | 160–175 cm | 2026-10-11 | 2026-10-14 | Complete | 2026-10-20
CTR-708593 | Atlanta, GA | Hispanic / Latino | Female | 18–34 | 153 | <160 cm | 2026-10-11 | 2026-10-14 | Complete | 2026-10-19
CTR-157836 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 172 | 160–175 cm | 2026-10-06 | 2026-10-14 | Complete | 2026-10-20
CTR-903267 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 164 | 160–175 cm | 2026-10-04 | 2026-10-16 | Complete | 2026-10-22
CTR-572340 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 165 | 160–175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-19
CTR-532442 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 166 | 160–175 cm | 2026-10-09 | 2026-10-14 | Complete | 2026-10-20
CTR-568996 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 165 | 160–175 cm | 2026-10-11 | 2026-10-14 | Complete | 2026-10-20
CTR-690270 | Atlanta, GA | Middle Eastern / North African | Male | 35–54 | 178 | >175 cm | 2026-10-09 | 2026-10-14 | Complete | 2026-10-19
CTR-885833 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 182 | >175 cm | 2026-10-11 | 2026-10-14 | Complete | 2026-10-19
CTR-441426 | Atlanta, GA | Asian (East, Southeast, Central) | Non-binary | 55+ | 176 | >175 cm | 2026-10-11 | 2026-10-14 | Complete | 2026-10-20
CTR-978749 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 179 | >175 cm | 2026-10-09 | 2026-10-14 | Complete | 2026-10-20
CTR-215231 | Atlanta, GA | Hispanic / Latino | Male | 55+ | 182 | >175 cm | 2026-10-07 | 2026-10-14 | Dropped
CTR-106175 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 165 | 160–175 cm | 2026-10-07 | 2026-10-14 | Complete | 2026-10-21
CTR-396560 | Atlanta, GA | European (Eastern, Western) | Male | 35–54 | 171 | 160–175 cm | 2026-10-09 | 2026-10-14 | Complete | 2026-10-20
CTR-650193 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 189 | >175 cm | 2026-10-10 | 2026-10-14 | Complete | 2026-10-20
CTR-868985 | Atlanta, GA | Black / African American / Caribbean | Non-binary | 18–34 | 179 | >175 cm | 2026-10-11 | 2026-10-15 | Complete | 2026-10-21
CTR-284681 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 55+ | 151 | <160 cm | 2026-10-11 | 2026-10-15 | Dropped
CTR-314014 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 155 | <160 cm | 2026-10-10 | 2026-10-15 | Active
CTR-471008 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 173 | 160–175 cm | 2026-10-05 | 2026-10-15 | Complete | 2026-10-20
CTR-264312 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 55+ | 155 | <160 cm | 2026-10-08 | 2026-10-15 | Complete | 2026-10-21
CTR-971280 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 169 | 160–175 cm | 2026-10-08 | 2026-10-15 | Complete | 2026-10-21
CTR-330215 | Atlanta, GA | Black / African American / Caribbean | Female | 18–34 | 164 | 160–175 cm | 2026-10-11 | 2026-10-15 | Complete | 2026-10-20
CTR-348335 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 178 | >175 cm | 2026-10-12 | 2026-10-15 | Complete | 2026-10-21
CTR-796225 | Atlanta, GA | European (Eastern, Western) | Male | 35–54 | 165 | 160–175 cm | 2026-10-06 | 2026-10-15 | Complete | 2026-10-21
CTR-702122 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 154 | <160 cm | 2026-10-12 | 2026-10-15 | Complete | 2026-10-21
CTR-191186 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 161 | 160–175 cm | 2026-10-10 | 2026-10-15 | Complete | 2026-10-20
CTR-867010 | Atlanta, GA | European (Eastern, Western) | Female | 55+ | 155 | <160 cm | 2026-10-05 | 2026-10-15 | Complete | 2026-10-20
CTR-214629 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 158 | <160 cm | 2026-10-09 | 2026-10-15 | Complete | 2026-10-20
CTR-736050 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 174 | 160–175 cm | 2026-10-06 | 2026-10-15 | Dropped
CTR-109524 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 175 | 160–175 cm | 2026-10-08 | 2026-10-15 | Complete | 2026-10-21
CTR-328559 | Atlanta, GA | Middle Eastern / North African | Female | 18–34 | 159 | <160 cm | 2026-10-09 | 2026-10-15 | Complete | 2026-10-20
CTR-394076 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 155 | <160 cm | 2026-10-08 | 2026-10-15 | Complete | 2026-10-20
CTR-404313 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 171 | 160–175 cm | 2026-10-09 | 2026-10-16 | Complete | 2026-10-23
CTR-910880 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 162 | 160–175 cm | 2026-10-06 | 2026-10-16 | Complete | 2026-10-22
CTR-566934 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 176 | >175 cm | 2026-10-13 | 2026-10-16 | Complete | 2026-10-22
CTR-118437 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 186 | >175 cm | 2026-10-09 | 2026-10-16 | Complete | 2026-10-22
CTR-963029 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 177 | >175 cm | 2026-10-12 | 2026-10-16 | Complete | 2026-10-23
CTR-862344 | Atlanta, GA | Middle Eastern / North African | Female | 55+ | 167 | 160–175 cm | 2026-10-08 | 2026-10-16 | Complete | 2026-10-23
CTR-353599 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 173 | 160–175 cm | 2026-10-08 | 2026-10-16 | Complete | 2026-10-22
CTR-134589 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 160 | 160–175 cm | 2026-10-10 | 2026-10-16 | Complete | 2026-10-22
CTR-193774 | Atlanta, GA | Middle Eastern / North African | Male | 35–54 | 171 | 160–175 cm | 2026-10-09 | 2026-10-16 | Complete | 2026-10-22
CTR-616536 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 166 | 160–175 cm | 2026-10-10 | 2026-10-16 | Complete | 2026-10-23
CTR-832268 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 180 | >175 cm | 2026-10-10 | 2026-10-16 | Complete | 2026-10-22
CTR-132233 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 175 | 160–175 cm | 2026-10-08 | 2026-10-16 | Complete | 2026-10-23
CTR-313492 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 183 | >175 cm | 2026-10-10 | 2026-10-16 | Complete | 2026-10-23
CTR-898914 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 159 | <160 cm | 2026-10-06 | 2026-10-16 | Complete | 2026-10-22
CTR-666492 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 154 | <160 cm | 2026-10-07 | 2026-10-16 | Complete | 2026-10-22
CTR-599605 | Atlanta, GA | Middle Eastern / North African | Female | 18–34 | 158 | <160 cm | 2026-10-07 | 2026-10-16 | Complete | 2026-10-22
CTR-123792 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 174 | 160–175 cm | 2026-10-13 | 2026-10-16 | Complete | 2026-10-22
CTR-422465 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 158 | <160 cm | 2026-10-16 | 2026-10-19 | Complete | 2026-10-23
CTR-518935 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 141 | <160 cm | 2026-10-13 | 2026-10-19 | Active
CTR-111005 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 151 | <160 cm | 2026-10-12 | 2026-10-19 | Complete | 2026-10-26
CTR-277078 | Atlanta, GA | Middle Eastern / North African | Female | 55+ | 162 | 160–175 cm | 2026-10-14 | 2026-10-19 | Dropped
CTR-855400 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 169 | 160–175 cm | 2026-10-10 | 2026-10-19 | Complete | 2026-10-23
CTR-990449 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 178 | >175 cm | 2026-10-13 | 2026-10-19 | Active
CTR-379039 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 175 | 160–175 cm | 2026-10-09 | 2026-10-19 | Dropped
CTR-310012 | Atlanta, GA | Middle Eastern / North African | Male | 18–34 | 186 | >175 cm | 2026-10-16 | 2026-10-19 | Complete | 2026-10-23
CTR-712372 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 177 | >175 cm | 2026-10-11 | 2026-10-19 | Complete | 2026-10-23
CTR-153070 | Atlanta, GA | European (Eastern, Western) | Female | 18–34 | 159 | <160 cm | 2026-10-12 | 2026-10-19 | Complete | 2026-10-26
CTR-754913 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 180 | >175 cm | 2026-10-16 | 2026-10-19 | Complete | 2026-10-26
CTR-179323 | Atlanta, GA | Black / African American / Caribbean | Male | 55+ | 159 | <160 cm | 2026-10-13 | 2026-10-19 | Complete | 2026-10-23
CTR-428485 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 178 | >175 cm | 2026-10-16 | 2026-10-19 | Complete | 2026-10-26
CTR-604606 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 159 | <160 cm | 2026-10-14 | 2026-10-19 | Active
CTR-154465 | Atlanta, GA | European (Eastern, Western) | Female | 18–34 | 170 | 160–175 cm | 2026-10-09 | 2026-10-19 | Active
CTR-867538 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 185 | >175 cm | 2026-10-14 | 2026-10-19 | Complete | 2026-10-23
CTR-898957 | Atlanta, GA | Hispanic / Latino | Male | 55+ | 177 | >175 cm | 2026-10-14 | 2026-10-19 | Complete | 2026-10-23
CTR-153651 | Atlanta, GA | European (Eastern, Western) | Male | 55+ | 179 | >175 cm | 2026-10-13 | 2026-10-19 | Complete | 2026-10-26
CTR-535553 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 160 | 160–175 cm | 2026-10-13 | 2026-10-21 | Active
CTR-567586 | Atlanta, GA | Middle Eastern / North African | Female | 18–34 | 167 | 160–175 cm | 2026-10-11 | 2026-10-19 | Complete | 2026-10-23
CTR-157032 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 55+ | 160 | 160–175 cm | 2026-10-13 | 2026-10-19 | Complete | 2026-10-23
CTR-360812 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 177 | >175 cm | 2026-10-14 | 2026-10-19 | Complete | 2026-10-23
CTR-305454 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 175 | 160–175 cm | 2026-10-15 | 2026-10-21 | Active
CTR-701719 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 148 | <160 cm | 2026-10-13 | 2026-10-21 | Active
CTR-407956 | Atlanta, GA | European (Eastern, Western) | Female | 55+ | 177 | >175 cm | 2026-10-15 | 2026-10-21 | Active
CTR-380220 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 159 | <160 cm | 2026-10-13 | 2026-10-21 | Active
CTR-190545 | Atlanta, GA | European (Eastern, Western) | Female | 18–34 | 164 | 160–175 cm | 2026-10-12 | 2026-10-21 | Active
CTR-187748 | Atlanta, GA | Hispanic / Latino | Female | 18–34 | 162 | 160–175 cm | 2026-10-15 | 2026-10-21 | Active
CTR-567381 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 171 | 160–175 cm | 2026-10-13 | 2026-10-21 | Active
CTR-498143 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 55+ | 155 | <160 cm | 2026-10-18 | 2026-10-21 | Active
CTR-942591 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 174 | 160–175 cm | 2026-10-13 | 2026-10-21 | Active
CTR-817116 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 167 | 160–175 cm | 2026-10-12 | 2026-10-21 | Active
CTR-598068 | Atlanta, GA | Hispanic / Latino | Male | 35–54 | 162 | 160–175 cm | 2026-10-14 | 2026-10-21 | Active
CTR-899138 | Atlanta, GA | Hispanic / Latino | Female | 35–54 | 163 | 160–175 cm | 2026-10-12 | 2026-10-21 | Active
CTR-161408 | Atlanta, GA | Middle Eastern / North African | Male | 18–34 | 173 | 160–175 cm | 2026-10-12 | 2026-10-21 | Active
CTR-307878 | Atlanta, GA | Hispanic / Latino | Female | 35–54 | 170 | 160–175 cm | 2026-10-12 | 2026-10-21 | Active
CTR-891974 | Atlanta, GA | Hispanic / Latino | Female | 35–54 | 157 | <160 cm | 2026-10-17 | 2026-10-21 | Dropped
CTR-700973 | Atlanta, GA | Middle Eastern / North African | Female | 55+ | 173 | 160–175 cm | 2026-10-17 | 2026-10-21 | Active
CTR-212075 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 156 | <160 cm | 2026-10-16 | 2026-10-21 | Active
CTR-659404 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 168 | 160–175 cm | 2026-10-11 | 2026-10-21 | Active
CTR-310604 | Atlanta, GA | Middle Eastern / North African | Male | 35–54 | 173 | 160–175 cm | 2026-10-18 | 2026-10-21 | Active
CTR-947946 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 170 | 160–175 cm | 2026-10-18 | 2026-10-21 | Active
CTR-248585 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 55+ | 168 | 160–175 cm | 2026-10-14 | 2026-10-21 | Active
CTR-873953 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 153 | <160 cm | 2026-10-17 | 2026-10-21 | Active
CTR-286871 | Atlanta, GA | Middle Eastern / North African | Female | 55+ | 165 | 160–175 cm | 2026-10-16 | 2026-10-22 | Active
CTR-319859 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 162 | 160–175 cm | 2026-10-17 | 2026-10-22 | Active
CTR-115285 | Atlanta, GA | Middle Eastern / North African | Male | 35–54 | 171 | 160–175 cm | 2026-10-15 | 2026-10-22 | Active
CTR-273710 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 173 | 160–175 cm | 2026-10-19 | 2026-10-22 | Active
CTR-387021 | Atlanta, GA | Hispanic / Latino | Female | 35–54 | 155 | <160 cm | 2026-10-18 | 2026-10-22 | Active
CTR-146409 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 177 | >175 cm | 2026-10-18 | 2026-10-22 | Active
CTR-182080 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 150 | <160 cm | 2026-10-14 | 2026-10-22 | Active
CTR-933092 | Atlanta, GA | Hispanic / Latino | Female | 18–34 | 170 | 160–175 cm | 2026-10-18 | 2026-10-22 | Active
CTR-209045 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 171 | 160–175 cm | 2026-10-12 | 2026-10-22 | Active
CTR-378503 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 164 | 160–175 cm | 2026-10-19 | 2026-10-22 | Active
CTR-992492 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 55+ | 181 | >175 cm | 2026-10-17 |  | Withdrew before start
CTR-970761 | Atlanta, GA | Middle Eastern / North African | Male | 18–34 | 163 | 160–175 cm | 2026-10-16 | 2026-10-22 | Active
CTR-692306 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 181 | >175 cm | 2026-10-18 | 2026-10-22 | Active
CTR-510440 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 165 | 160–175 cm | 2026-10-13 | 2026-10-22 | Active
CTR-558892 | Atlanta, GA | Middle Eastern / North African | Female | 18–34 | 170 | 160–175 cm | 2026-10-12 | 2026-10-22 | Active
CTR-904067 | Atlanta, GA | Hispanic / Latino | Female | 35–54 | 161 | 160–175 cm | 2026-10-15 | 2026-10-22 | Active
CTR-782499 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 169 | 160–175 cm | 2026-10-16 | 2026-10-22 | Active
CTR-203227 | Atlanta, GA | Black / African American / Caribbean | Female | 18–34 | 153 | <160 cm | 2026-10-13 | 2026-10-22 | Active
CTR-546604 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 141 | <160 cm | 2026-10-15 | 2026-10-22 | Active
CTR-608926 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 173 | 160–175 cm | 2026-10-19 | 2026-10-22 | Active
CTR-377231 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 174 | 160–175 cm | 2026-10-17 | 2026-10-22 | Active
CTR-266255 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 168 | 160–175 cm | 2026-10-14 | 2026-10-22 | Active
CTR-214704 | Atlanta, GA | Black / African American / Caribbean | Female | 55+ | 147 | <160 cm | 2026-10-14 | 2026-10-23 | Active
CTR-558478 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 170 | 160–175 cm | 2026-10-15 | 2026-10-23 | Active
CTR-288751 | Atlanta, GA | European (Eastern, Western) | Male | 18–34 | 168 | 160–175 cm | 2026-10-15 | 2026-10-23 | Active
CTR-458092 | Atlanta, GA | Hispanic / Latino | Male | 55+ | 178 | >175 cm | 2026-10-15 | 2026-10-23 | Active
CTR-138837 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 172 | 160–175 cm | 2026-10-15 | 2026-10-23 | Active
CTR-505428 | Atlanta, GA | Hispanic / Latino | Male | 55+ | 172 | 160–175 cm | 2026-10-15 | 2026-10-23 | Active
CTR-698380 | Atlanta, GA | European (Eastern, Western) | Male | 55+ | 178 | >175 cm | 2026-10-16 | 2026-10-23 | Active
CTR-228347 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 155 | <160 cm | 2026-10-17 | 2026-10-23 | Active
CTR-544855 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 185 | >175 cm | 2026-10-20 | 2026-10-23 | Active
CTR-679580 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 169 | 160–175 cm | 2026-10-13 | 2026-10-23 | Active
CTR-281452 | Atlanta, GA | European (Eastern, Western) | Male | 35–54 | 176 | >175 cm | 2026-10-20 | 2026-10-23 | Active
CTR-470615 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 168 | 160–175 cm | 2026-10-14 | 2026-10-23 | Active
CTR-645950 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 167 | 160–175 cm | 2026-10-13 | 2026-10-23 | Active
CTR-385177 | Atlanta, GA | Black / African American / Caribbean | Female | 18–34 | 153 | <160 cm | 2026-10-13 | 2026-10-23 | Active
CTR-813943 | Atlanta, GA | Middle Eastern / North African | Female | 35–54 | 159 | <160 cm | 2026-10-18 | 2026-10-23 | Active
CTR-342392 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 18–34 | 191 | >175 cm | 2026-10-20 | 2026-10-23 | Active
CTR-292768 | Atlanta, GA | Black / African American / Caribbean | Female | 55+ | 156 | <160 cm | 2026-10-18 | 2026-10-23 | Active
CTR-737494 | Atlanta, GA | Hispanic / Latino | Female | 18–34 | 162 | 160–175 cm | 2026-10-15 | 2026-10-23 | Active
CTR-473983 | Atlanta, GA | Black / African American / Caribbean | Male | 35–54 | 174 | 160–175 cm | 2026-10-16 | 2026-10-23 | Active
CTR-738444 | Atlanta, GA | Black / African American / Caribbean | Female | 55+ | 163 | 160–175 cm | 2026-10-17 | 2026-10-23 | Active
CTR-269169 | Atlanta, GA | Hispanic / Latino | Female | 35–54 | 156 | <160 cm | 2026-10-18 | 2026-10-23 | Active
CTR-119228 | Atlanta, GA | European (Eastern, Western) | Male | 35–54 | 173 | 160–175 cm | 2026-10-19 | 2026-10-23 | Active
CTR-449652 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 164 | 160–175 cm | 2026-10-19 |  | Booked
CTR-266976 | Atlanta, GA | Hispanic / Latino | Male | 55+ | 177 | >175 cm | 2026-10-21 |  | Booked
CTR-587160 | Atlanta, GA | Middle Eastern / North African | Male | 55+ | 177 | >175 cm | 2026-10-17 |  | Booked
CTR-721577 | Atlanta, GA | Black / African American / Caribbean | Female | 35–54 | 153 | <160 cm | 2026-10-16 |  | Booked
CTR-516156 | Atlanta, GA | Black / African American / Caribbean | Male | 18–34 | 173 | 160–175 cm | 2026-10-23 |  | Booked
CTR-970305 | Atlanta, GA | European (Eastern, Western) | Female | 18–34 | 166 | 160–175 cm | 2026-10-22 |  | Booked
CTR-996098 | Atlanta, GA | European (Eastern, Western) | Male | 55+ | 164 | 160–175 cm | 2026-10-19 |  | Booked
CTR-430508 | Atlanta, GA | European (Eastern, Western) | Male | 35–54 | 175 | 160–175 cm | 2026-10-21 |  | Booked
CTR-551137 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 175 | 160–175 cm | 2026-10-18 |  | Booked
CTR-507189 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 173 | 160–175 cm | 2026-10-20 |  | Booked
CTR-846724 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 184 | >175 cm | 2026-10-21 |  | Booked
CTR-376597 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 55+ | 168 | 160–175 cm | 2026-10-16 |  | Booked
CTR-986285 | Atlanta, GA | Black / African American / Caribbean | Female | 18–34 | 159 | <160 cm | 2026-10-17 |  | Booked
CTR-919299 | Atlanta, GA | European (Eastern, Western) | Female | 35–54 | 170 | 160–175 cm | 2026-10-17 |  | Booked
CTR-453453 | Atlanta, GA | Hispanic / Latino | Male | 18–34 | 176 | >175 cm | 2026-10-16 |  | Booked
CTR-146861 | Atlanta, GA | Asian (East, Southeast, Central) | Male | 35–54 | 170 | 160–175 cm | 2026-10-20 |  | Booked
CTR-591008 | Atlanta, GA | Hispanic / Latino | Female | 55+ | 166 | 160–175 cm | 2026-10-23 |  | Booked
CTR-489876 | Atlanta, GA | European (Eastern, Western) | Male | 35–54 | 169 | 160–175 cm | 2026-10-18 |  | Booked
CTR-860735 | Atlanta, GA | Black / African American / Caribbean | Female | 55+ | 169 | 160–175 cm | 2026-10-19 |  | Booked
CTR-627825 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 35–54 | 159 | <160 cm | 2026-10-21 |  | Booked
CTR-869656 | Atlanta, GA | Asian (East, Southeast, Central) | Female | 18–34 | 158 | <160 cm | 2026-10-21 |  | Booked

## Sessions
Session ID | Participant ID | Site | Date | Production day | Day | Slot | Session type | Station | Lighting | Supervisor ID | Supervisor | Device ID | Lux | Showed up | Selfie task | Device task | Upload confirmed | Client QC sampled | Client QC reviewed | Client QC result | Notes
SES-261012-101 | CTR-536794 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1280 | Y | Pass | Pass | Y | N
SES-261012-201 | CTR-876409 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Pass | Pass | Y | Y | Y | Fail
SES-261012-301 | CTR-620149 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 600 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261012-401 | CTR-249673 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 95 | Y | Pass | Pass | Y | N
SES-261012-102 | CTR-899832 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1040 | Y | Pass | Pass | Y | N
SES-261012-202 | CTR-443006 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 555 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261012-302 | CTR-773171 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 430 | Y | Pass | Pass | Y | N
SES-261012-402 | CTR-480215 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 09:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 190 | Y | Pass | Pass | Y | N
SES-261012-103 | CTR-691441 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 515 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261012-203 | CTR-590976 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Pass | Pass | Y | N
SES-261012-303 | CTR-873116 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 500 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261012-403 | CTR-770027 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 105 | Y | Pass | Pass | Y | N
SES-261012-104 | CTR-889917 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 770 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261012-204 | CTR-489966 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 550 | Y | Pass | Pass | Y | N
SES-261012-304 | CTR-764637 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 675 | Y | Pass | Pass | Y | N
SES-261012-404 | CTR-605004 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 10:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 120 | Y | Pass | Pass | Y | N
SES-261012-105 | CTR-682433 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 935 | Y | Pass | Pass | Y | N
SES-261012-205 | CTR-222413 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 485 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261012-305 | CTR-360020 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 275 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261012-405 | CTR-139974 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 160 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261012-106 | CTR-479835 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1110 | Y | Pass | Pass | Y | N
SES-261012-206 | CTR-401194 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 420 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261012-306 | CTR-357954 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 585 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261012-406 | CTR-581574 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 11:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 125 | Y | Pass | Pass | Y | N
SES-261012-107 | CTR-858494 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1130 | Y | Pass | Pass | Y | N
SES-261012-207 | CTR-731921 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261012-307 | CTR-493627 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 515 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261012-407 | CTR-997935 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 180 | Y | Pass | Pass | Y | N
SES-261012-108 | CTR-844268 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 720 | Y | Pass | Pass | Y | N
SES-261012-208 | CTR-316031 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 500 | Y | Pass | Pass | Y | N
SES-261012-308 | CTR-537205 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 460 | Y | Pass | Pass | Y | N
SES-261012-408 | CTR-889146 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 135 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261012-109 | CTR-531995 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 740 | Y | Pass | Pass | Y | N
SES-261012-209 | CTR-183971 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261012-309 | CTR-746884 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 725 | Y | Pass | Pass | Y | N
SES-261012-409 | CTR-570285 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 170 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261012-110 | CTR-990459 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 845 | Y | Pass | Pass | Y | N
SES-261012-210 | CTR-660542 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 510 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261012-310 | CTR-852337 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 390 | Y | Pass | Pass | Y | N
SES-261012-410-NS34 | CTR-321217 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:30 | Session 1 | ST-4 | Warm / low light |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261012-410 | CTR-976324 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 14:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 110 | Y | Pass | Pass | Y | N
SES-261012-111 | CTR-790282 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 15:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 455 | Y | Pass | Pass | Y | N
SES-261012-211 | CTR-415425 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 15:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 435 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261012-311 | CTR-942159 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 15:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 315 | Y | Pass | Pass | Y | N
SES-261012-411 | CTR-927040 | Atlanta, GA | 2026-10-12 | 1 | W3 Mon | 15:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 125 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261014-101 | CTR-249673 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1260 | Y | Pass | Pass | Y | N
SES-261014-201 | CTR-536794 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 510 | Y | Pass | Pass | Y | N
SES-261014-301 | CTR-443006 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 285 | Y | Pass | Pass | Y | N
SES-261014-401 | CTR-590976 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 180 | Y | Pass | Pass | Y | N
SES-261014-102 | CTR-222413 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 765 | Y | Pass | Pass | Y | N
SES-261014-202 | CTR-682433 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 485 | Y | Pass | Pass | Y | N
SES-261014-302 | CTR-479835 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 735 | Y | Pass | Pass | Y | N
SES-261014-402 | CTR-493627 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 150 | Y | Pass | Pass | Y | N
SES-261014-103 | CTR-581574 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 760 | Y | Pass | Pass | Y | N
SES-261014-203 | CTR-942159 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 485 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261014-303 | CTR-122934 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 605 | Y | Pass | Pass | Y | N
SES-261014-403 | CTR-710363 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 105 | Y | Fail | Fail | Y | N |  |  | Retaken on the spot: selfie + device task
SES-261014-104 | CTR-942442 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 650 | Y | Pass | Pass | Y | N
SES-261014-204 | CTR-420748 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 455 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261014-304 | CTR-993230 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 330 | Y | Pass | Pass | Y | N
SES-261014-404 | CTR-661915 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 10:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 100 | Y | Pass | Pass | Y | N
SES-261014-105 | CTR-434783 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 815 | Y | Pass | Pass | Y | N
SES-261014-205 | CTR-283977 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 470 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261014-305 | CTR-396867 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 730 | Y | Pass | Pass | Y | N
SES-261014-405 | CTR-436935 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 105 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261014-106 | CTR-762193 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1320 | Y | Pass | Pass | Y | N
SES-261014-206 | CTR-697809 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 495 | Y | Pass | Pass | Y | N
SES-261014-306-NS26 | CTR-476209 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:30 | Session 1 | ST-3 | Mixed |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261014-306 | CTR-787855 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 425 | Y | Pass | Pass | Y | N
SES-261014-406 | CTR-215875 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 11:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 185 | Y | Pass | Pass | Y | N
SES-261014-107 | CTR-708593 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1360 | Y | Pass | Pass | Y | N
SES-261014-207 | CTR-157836 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 425 | Y | Pass | Pass | Y | N
SES-261014-307-NS87 | CTR-903267 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:00 | Session 1 | ST-3 | Mixed |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261014-307 | CTR-572340 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 710 | Y | Pass | Pass | Y | N
SES-261014-407 | CTR-532442 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 120 | Y | Pass | Pass | Y | N
SES-261014-108 | CTR-568996 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 905 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261014-208 | CTR-690270 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 465 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261014-308 | CTR-885833 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 745 | Y | Pass | Pass | Y | N
SES-261014-408 | CTR-441426 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 165 | Y | Pass | Pass | Y | N
SES-261014-109 | CTR-978749 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 975 | Y | Pass | Pass | Y | N
SES-261014-209 | CTR-215231 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 430 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261014-309 | CTR-106175 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 14:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 480 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261014-409 | CTR-396560 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 110 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261014-110 | CTR-650193 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 470 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261014-210 | CTR-321217 | Atlanta, GA | 2026-10-14 | 2 | W3 Wed | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 555 | Y | Pass | Pass | Y | N
SES-261015-101 | CTR-876409 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 465 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-201 | CTR-620149 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 545 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-301 | CTR-899832 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 535 | Y | Pass | Pass | Y | N
SES-261015-401 | CTR-773171 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 155 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-102 | CTR-480215 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1395 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261015-202-NS36 | CTR-691441 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:30 | Session 2 | ST-2 | Overhead artificial |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261015-202 | CTR-873116 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 500 | Y | Pass | Pass | Y | N
SES-261015-302 | CTR-770027 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 265 | Y | Pass | Pass | Y | N
SES-261015-402-NS22 | CTR-889917 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:30 | Session 2 | ST-4 | Warm / low light |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261015-402 | CTR-489966 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 120 | Y | Pass | Pass | Y | N
SES-261015-103 | CTR-764637 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 775 | Y | Pass | Pass | Y | N
SES-261015-203 | CTR-605004 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 470 | Y | Pass | Pass | Y | N
SES-261015-303 | CTR-139974 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 715 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261015-403 | CTR-360020 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 155 | Y | Pass | Pass | Y | N
SES-261015-104 | CTR-401194 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1130 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261015-204 | CTR-357954 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 495 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-304 | CTR-858494 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 395 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-404 | CTR-731921 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 10:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 145 | Y | Pass | Pass | Y | N
SES-261015-105 | CTR-997935 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1015 | Y | Pass | Pass | Y | N
SES-261015-205 | CTR-844268 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 450 | Y | Pass | Pass | Y | N
SES-261015-305 | CTR-316031 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 605 | Y | Pass | Pass | Y | N
SES-261015-405 | CTR-537205 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 155 | Y | Pass | Pass | Y | N
SES-261015-106 | CTR-889146 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 835 | Y | Pass | Pass | Y | N
SES-261015-206 | CTR-531995 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 450 | Y | Pass | Pass | Y | N
SES-261015-306 | CTR-183971 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 295 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-406 | CTR-746884 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 11:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 95 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-107 | CTR-570285 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 825 | Y | Pass | Pass | Y | N
SES-261015-207 | CTR-990459 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 450 | Y | Pass | Pass | Y | N
SES-261015-307 | CTR-660542 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 445 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261015-407 | CTR-868985 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 140 | Y | Pass | Pass | Y | N
SES-261015-108 | CTR-284681 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 1090 | Y | Pass | Pass | Y | N
SES-261015-208 | CTR-314014 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 545 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-308 | CTR-471008 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 420 | Y | Pass | Pass | Y | N
SES-261015-408 | CTR-264312 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 145 | Y | Pass | Pass | Y | N
SES-261015-109 | CTR-971280 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 575 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-209 | CTR-330215 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 545 | Y | Pass | Pass | Y | N
SES-261015-309 | CTR-348335 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 475 | Y | Pass | Pass | Y | N
SES-261015-409 | CTR-796225 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 140 | Y | Pass | Pass | Y | N
SES-261015-110 | CTR-702122 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 615 | Y | Pass | Pass | Y | N
SES-261015-210 | CTR-191186 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Pass | Pass | Y | N
SES-261015-310 | CTR-867010 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 630 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261015-410 | CTR-214629 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 14:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 180 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-111 | CTR-736050 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 15:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 910 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261015-211 | CTR-109524 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 15:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 560 | Y | Pass | Pass | Y | N
SES-261015-311 | CTR-328559 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 15:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 650 | Y | Pass | Pass | Y | N
SES-261015-411 | CTR-394076 | Atlanta, GA | 2026-10-15 | 3 | W3 Thu | 15:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 110 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-101 | CTR-852337 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 970 | Y | Pass | Pass | Y | N
SES-261016-201 | CTR-976324 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Pass | Pass | Y | N
SES-261016-301 | CTR-790282 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 395 | Y | Pass | Pass | Y | N
SES-261016-401 | CTR-415425 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 125 | Y | Pass | Pass | Y | N
SES-261016-102 | CTR-927040 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 975 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-202 | CTR-122934 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 460 | Y | Pass | Pass | Y | N
SES-261016-302 | CTR-710363 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 690 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-402 | CTR-942442 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 135 | Y | Pass | Pass | Y | N
SES-261016-103 | CTR-420748 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 595 | Y | Pass | Pass | Y | N
SES-261016-203-NS38 | CTR-993230 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:00 | Session 2 | ST-2 | Overhead artificial |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261016-203 | CTR-661915 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 475 | Y | Pass | Pass | Y | N
SES-261016-303 | CTR-434783 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 575 | Y | Pass | Pass | Y | N
SES-261016-403 | CTR-283977 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 100 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-104 | CTR-396867 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 460 | Y | Pass | Pass | Y | N
SES-261016-204 | CTR-436935 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 490 | Y | Pass | Pass | Y | N
SES-261016-304 | CTR-762193 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 725 | Y | Pass | Pass | Y | N
SES-261016-404 | CTR-697809 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 10:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 170 | Y | Pass | Pass | Y | N
SES-261016-105 | CTR-787855 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 530 | Y | Pass | Pass | Y | N
SES-261016-205 | CTR-215875 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 505 | Y | Pass | Pass | Y | N
SES-261016-305 | CTR-708593 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:00 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 780 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261016-405 | CTR-157836 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:00 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 90 | Y | Pass | Pass | Y | N
SES-261016-106 | CTR-572340 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:30 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 960 | Y | Pass | Pass | Y | N
SES-261016-206 | CTR-532442 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:30 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 490 | Y | Pass | Pass | Y | N
SES-261016-306 | CTR-568996 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:30 | Session 2 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 475 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261016-406 | CTR-690270 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 11:30 | Session 2 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 105 | Y | Pass | Pass | Y | N
SES-261016-107 | CTR-885833 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:00 | Session 2 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 965 | Y | Pass | Pass | Y | N
SES-261016-207 | CTR-441426 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:00 | Session 2 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 555 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261016-307 | CTR-404313 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 730 | Y | Pass | Pass | Y | N
SES-261016-407 | CTR-910880 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 185 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261016-108 | CTR-566934 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 455 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261016-208 | CTR-118437 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 455 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-308 | CTR-963029 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 710 | Y | Pass | Pass | Y | N
SES-261016-408 | CTR-862344 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 175 | Y | Pass | Pass | Y | N
SES-261016-109 | CTR-353599 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 730 | Y | Pass | Pass | Y | N
SES-261016-209 | CTR-134589 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 435 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-309 | CTR-193774 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 280 | Y | Pass | Pass | Y | N
SES-261016-409 | CTR-616536 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 160 | Y | Pass | Pass | Y | N
SES-261016-110 | CTR-832268 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 355 | Y | Pass | Pass | Y | N
SES-261016-210 | CTR-132233 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 545 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-310 | CTR-313492 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:30 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 335 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-410 | CTR-898914 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 14:30 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 95 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-111 | CTR-666492 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 15:00 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 615 | Y | Pass | Pass | Y | N
SES-261016-211 | CTR-599605 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 15:00 | Session 1 | ST-2 | Overhead artificial | SUP-B | Marcus Bell | DEV-02 | 495 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261016-311 | CTR-123792 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 15:00 | Session 1 | ST-3 | Mixed | SUP-C | Lena Okafor | DEV-03 | 355 | Y | Pass | Pass | Y | N
SES-261016-411 | CTR-476209 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 15:00 | Session 1 | ST-4 | Warm / low light | SUP-D | Tomas Haddad | DEV-04 | 105 | Y | Pass | Pass | Y | N
SES-261016-112 | CTR-903267 | Atlanta, GA | 2026-10-16 | 4 | W3 Fri | 15:30 | Session 1 | ST-1 | Natural (window) | SUP-A | Priya Nair | DEV-01 | 370 | Y | Pass | Pass | Y | N
SES-261019-101-NS37 | CTR-215231 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:00 | Session 2 | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261019-101 | CTR-106175 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1025 | Y | Pass | Pass | Y | N
SES-261019-201 | CTR-978749 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 430 | Y | Pass | Pass | Y | N
SES-261019-301 | CTR-876409 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:00 | Makeup | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 690 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-401 | CTR-650193 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 145 | Y | Pass | Pass | Y | N
SES-261019-102 | CTR-396560 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 480 | Y | Pass | Pass | Y | N
SES-261019-202 | CTR-868985 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 545 | Y | Pass | Pass | Y | N
SES-261019-302 | CTR-321217 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 470 | Y | Pass | Pass | Y | N
SES-261019-402-NS48 | CTR-284681 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:30 | Session 2 | ST-4 | Warm / low light |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261019-402 | CTR-314014 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 175 | Y | Pass | Pass | Y | Y | Y | Fail
SES-261019-103 | CTR-471008 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 860 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261019-203 | CTR-264312 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 475 | Y | Pass | Pass | Y | N
SES-261019-303 | CTR-971280 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 540 | Y | Pass | Pass | Y | N
SES-261019-403 | CTR-330215 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 95 | Y | Pass | Pass | Y | N
SES-261019-104 | CTR-348335 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 550 | Y | Pass | Pass | Y | N
SES-261019-204 | CTR-796225 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 510 | Y | Pass | Pass | Y | N
SES-261019-304 | CTR-702122 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 340 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261019-404 | CTR-191186 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 10:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 135 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-105 | CTR-867010 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 645 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261019-205 | CTR-214629 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 530 | Y | Pass | Pass | Y | N
SES-261019-305-NS86 | CTR-736050 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:00 | Session 2 | ST-3 | Mixed |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261019-305 | CTR-109524 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 460 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261019-405 | CTR-328559 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 190 | Y | Pass | Pass | Y | N
SES-261019-106 | CTR-394076 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 535 | Y | Pass | Pass | Y | N
SES-261019-206 | CTR-422465 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 555 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261019-306 | CTR-518935 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 510 | Y | Pass | Pass | Y | N
SES-261019-406 | CTR-111005 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 11:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 165 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-107 | CTR-277078 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1275 | Y | Pass | Pass | Y | N
SES-261019-207 | CTR-855400 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 515 | Y | Pass | Pass | Y | N
SES-261019-307 | CTR-990449 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 410 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261019-407 | CTR-379039 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 115 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-108 | CTR-310012 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 595 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-208 | CTR-712372 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 450 | Y | Pass | Pass | Y | N
SES-261019-308 | CTR-153070 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 610 | Y | Pass | Pass | Y | N
SES-261019-408 | CTR-754913 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 180 | Y | Pass | Pass | Y | N
SES-261019-109 | CTR-179323 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 390 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-209 | CTR-428485 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 450 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-309 | CTR-604606 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 645 | Y | Pass | Pass | Y | N
SES-261019-409 | CTR-154465 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 135 | Y | Pass | Pass | Y | N
SES-261019-110 | CTR-867538 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 930 | Y | Pass | Pass | Y | N
SES-261019-210 | CTR-898957 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 470 | Y | Pass | Pass | Y | N
SES-261019-310 | CTR-153651 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 595 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261019-410-NS78 | CTR-535553 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:30 | Session 1 | ST-4 | Warm / low light |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261019-410 | CTR-567586 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 14:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 150 | Y | Pass | Pass | Y | N
SES-261019-111 | CTR-157032 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 15:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 325 | Y | Pass | Pass | Y | N
SES-261019-211 | CTR-360812 | Atlanta, GA | 2026-10-19 | 5 | W4 Mon | 15:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 435 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261021-101 | CTR-404313 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 575 | Y | Pass | Pass | Y | N
SES-261021-201 | CTR-910880 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 545 | Y | Pass | Pass | Y | N
SES-261021-301 | CTR-132233 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 630 | Y | Pass | Pass | Y | N
SES-261021-401 | CTR-566934 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 105 | Y | Pass | Pass | Y | N
SES-261021-102 | CTR-118437 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 890 | Y | Pass | Pass | Y | N
SES-261021-202 | CTR-963029 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 540 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261021-302 | CTR-599605 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 575 | Y | Pass | Pass | Y | N
SES-261021-402 | CTR-353599 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 170 | Y | Pass | Pass | Y | N
SES-261021-103 | CTR-862344 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1005 | Y | Pass | Pass | Y | N
SES-261021-203 | CTR-193774 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 435 | Y | Pass | Pass | Y | N
SES-261021-303 | CTR-701719 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 440 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261021-403 | CTR-134589 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 130 | Y | Pass | Pass | Y | N
SES-261021-104 | CTR-616536 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1035 | Y | Pass | Pass | Y | N
SES-261021-204 | CTR-832268 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 545 | Y | Pass | Pass | Y | N
SES-261021-304 | CTR-187748 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 650 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261021-404 | CTR-313492 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 10:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 95 | Y | Pass | Pass | Y | N
SES-261021-105 | CTR-898914 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1260 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261021-205 | CTR-666492 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 540 | Y | Pass | Pass | Y | N
SES-261021-305 | CTR-817116 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-03 | 690 | Y | Pass | Pass | Y | N
SES-261021-405 | CTR-123792 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 110 | Y | Pass | Pass | Y | N
SES-261021-106-NS38 | CTR-476209 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:30 | Session 2 | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261021-106 | CTR-305454 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 555 | Y | Pass | Pass | Y | N
SES-261021-206 | CTR-903267 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 425 | Y | Pass | Pass | Y | N
SES-261021-406 | CTR-407956 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 11:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 185 | Y | Pass | Pass | Y | N
SES-261021-107 | CTR-380220 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 13:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1195 | Y | Pass | Pass | Y | N
SES-261021-207 | CTR-190545 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 13:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 500 | Y | Pass | Pass | Y | N
SES-261021-407 | CTR-567381 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 125 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261021-108 | CTR-498143 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1215 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261021-208 | CTR-942591 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 495 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261021-408 | CTR-598068 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 170 | Y | Pass | Pass | Y | N
SES-261021-109 | CTR-899138 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 945 | Y | Pass | Pass | Y | N
SES-261021-209 | CTR-161408 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 525 | Y | Pass | Pass | Y | N
SES-261021-309 | CTR-307878 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 345 | Y | Pass | Pass | Y | N
SES-261021-409 | CTR-891974 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 170 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261021-110 | CTR-700973 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 575 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261021-210 | CTR-212075 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 540 | Y | Pass | Pass | Y | N
SES-261021-310 | CTR-659404 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 760 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261021-410 | CTR-310604 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 14:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 110 | Y | Pass | Pass | Y | N
SES-261021-111 | CTR-947946 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 15:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 435 | Y | Pass | Pass | Y | N
SES-261021-211 | CTR-248585 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 15:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 545 | Y | Pass | Pass | Y | N
SES-261021-311 | CTR-873953 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 15:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 480 | Y | Pass | Pass | Y | N
SES-261021-411 | CTR-535553 | Atlanta, GA | 2026-10-21 | 6 | W4 Wed | 15:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 145 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261022-101-NS53 | CTR-314014 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:00 | Makeup | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261022-101 | CTR-422465 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1175 | Y | Pass | Pass | Y | N
SES-261022-201 | CTR-518935 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 485 | Y | Pass | Pass | Y | Y | N
SES-261022-301 | CTR-111005 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 690 | Y | Fail | Pass | Y | N |  |  | Retaken on the spot: selfie task
SES-261022-401-NS59 | CTR-277078 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:00 | Session 2 | ST-4 | Warm / low light |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261022-401 | CTR-855400 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 135 | Y | Pass | Pass | Y | N
SES-261022-102 | CTR-990449 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 455 | Y | Pass | Pass | Y | Y | N
SES-261022-202-NS79 | CTR-379039 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:30 | Session 2 | ST-2 | Overhead artificial |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261022-202 | CTR-310012 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 480 | Y | Pass | Pass | Y | N
SES-261022-302 | CTR-712372 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 720 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261022-402 | CTR-153070 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 165 | Y | Pass | Pass | Y | N
SES-261022-103 | CTR-754913 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 895 | Y | Pass | Pass | Y | N
SES-261022-203 | CTR-179323 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 550 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261022-303 | CTR-428485 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 640 | Y | Pass | Pass | Y | N
SES-261022-403 | CTR-604606 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 120 | Y | Pass | Pass | Y | Y | N
SES-261022-104-NS14 | CTR-154465 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:30 | Session 2 | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261022-104 | CTR-898957 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 845 | Y | Pass | Pass | Y | N
SES-261022-204 | CTR-867538 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 520 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261022-304 | CTR-567586 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 410 | Y | Pass | Pass | Y | N
SES-261022-404 | CTR-153651 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 10:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 170 | Y | Pass | Pass | Y | N
SES-261022-105 | CTR-360812 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 930 | Y | Pass | Pass | Y | N
SES-261022-205 | CTR-157032 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 505 | Y | Pass | Pass | Y | N
SES-261022-305 | CTR-286871 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 525 | Y | Pass | Pass | Y | N
SES-261022-405 | CTR-319859 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 125 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261022-106 | CTR-115285 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 945 | Y | Pass | Pass | Y | N
SES-261022-206 | CTR-273710 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 465 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261022-306 | CTR-387021 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 280 | Y | Fail | Pass | Y | Y | Y | Pass | Retaken on the spot: selfie task
SES-261022-406 | CTR-146409 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 11:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 185 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261022-107 | CTR-182080 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 525 | Y | Pass | Pass | Y | N
SES-261022-207 | CTR-933092 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 530 | Y | Pass | Pass | Y | N
SES-261022-307 | CTR-209045 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 315 | Y | Pass | Pass | Y | Y | N
SES-261022-407 | CTR-378503 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 120 | Y | Pass | Pass | Y | Y | Y | Pass
SES-261022-108-NS66 | CTR-992492 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:30 | Session 1 | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261022-108 | CTR-970761 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 610 | Y | Pass | Pass | Y | N
SES-261022-208 | CTR-692306 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 495 | Y | Pass | Pass | Y | Y | N
SES-261022-308 | CTR-510440 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 440 | Y | Pass | Pass | Y | N
SES-261022-408 | CTR-558892 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 130 | Y | Pass | Fail | Y | Y | Y | Pass | Retaken on the spot: device task
SES-261022-109 | CTR-904067 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 660 | Y | Pass | Pass | Y | Y | N
SES-261022-209 | CTR-782499 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 545 | Y | Pass | Pass | Y | N
SES-261022-309 | CTR-203227 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 570 | Y | Pass | Pass | Y | N
SES-261022-409 | CTR-546604 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 95 | Y | Pass | Pass | Y | N
SES-261022-110 | CTR-608926 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 840 | Y | Pass | Pass | Y | Y | N
SES-261022-210 | CTR-377231 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 525 | Y | Pass | Pass | Y | N
SES-261022-310 | CTR-266255 | Atlanta, GA | 2026-10-22 | 7 | W4 Thu | 14:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 345 | Y | Pass | Pass | Y | N
SES-261023-101 | CTR-701719 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 745 | Y | Pass | Pass | Y | N
SES-261023-201 | CTR-305454 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 420 | Y | Pass | Pass | Y | N
SES-261023-301 | CTR-407956 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 355 | Y | Pass | Pass | Y | N
SES-261023-401-NS62 | CTR-380220 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:00 | Session 2 | ST-4 | Warm / low light |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261023-401 | CTR-190545 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 180 | Y | Pass | Pass | Y | Y | N
SES-261023-102 | CTR-187748 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 560 | Y | Pass | Pass | Y | Y | N
SES-261023-202 | CTR-567381 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 455 | Y | Pass | Pass | Y | N
SES-261023-302 | CTR-498143 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 335 | Y | Pass | Pass | Y | N
SES-261023-402 | CTR-942591 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 09:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 170 | Y | Pass | Pass | Y | N
SES-261023-103-NS93 | CTR-817116 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:00 | Session 2 | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261023-103 | CTR-598068 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1155 | Y | Pass | Pass | Y | N
SES-261023-203 | CTR-899138 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 540 | Y | Pass | Pass | Y | N
SES-261023-303 | CTR-161408 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:00 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 585 | Y | Pass | Pass | Y | Y | N
SES-261023-403 | CTR-307878 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:00 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 145 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261023-104-NS23 | CTR-891974 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:30 | Session 2 | ST-1 | Natural (window) |  |  |  |  | N | [6 empty] | No-show; withdrew from collection
SES-261023-104 | CTR-212075 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:30 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1170 | Y | Pass | Pass | Y | Y | N
SES-261023-204 | CTR-700973 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:30 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 555 | Y | Pass | Pass | Y | N
SES-261023-304 | CTR-310604 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:30 | Session 2 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 310 | Y | Pass | Pass | Y | Y | N
SES-261023-404 | CTR-659404 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 10:30 | Session 2 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 125 | Y | Pass | Pass | Y | N
SES-261023-105 | CTR-248585 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:00 | Session 2 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 740 | Y | Pass | Pass | Y | N
SES-261023-205-NS35 | CTR-947946 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:00 | Session 2 | ST-2 | Overhead artificial |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261023-205 | CTR-873953 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:00 | Session 2 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 505 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261023-305-NS39 | CTR-535553 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:00 | Session 2 | ST-3 | Mixed |  |  |  |  | N | [6 empty] | No-show; rebooked
SES-261023-305 | CTR-314014 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:00 | Makeup | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 770 | Y | Pass | Pass | Y | N
SES-261023-405 | CTR-214704 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 185 | Y | Pass | Pass | Y | N
SES-261023-106 | CTR-558478 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 680 | Y | Pass | Pass | Y | N
SES-261023-206 | CTR-288751 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 525 | Y | Pass | Pass | Y | N
SES-261023-306 | CTR-458092 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 415 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261023-406 | CTR-138837 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 11:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 125 | Y | Pass | Pass | Y | N
SES-261023-107 | CTR-505428 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 1315 | Y | Pass | Pass | Y | N
SES-261023-207 | CTR-698380 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 500 | Y | Pass | Pass | Y | N
SES-261023-307 | CTR-228347 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 455 | Y | Pass | Pass | Y | N
SES-261023-407 | CTR-544855 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 180 | Y | Pass | Pass | Y | N
SES-261023-108 | CTR-679580 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 480 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261023-208 | CTR-281452 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 445 | Y | Pass | Pass | Y | Y | N
SES-261023-308 | CTR-470615 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 330 | Y | Pass | Fail | Y | Y | N |  | Retaken on the spot: device task
SES-261023-408 | CTR-645950 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 13:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 180 | Y | Pass | Pass | Y | N
SES-261023-109 | CTR-385177 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 920 | Y | Pass | Pass | Y | N
SES-261023-209 | CTR-813943 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:00 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 505 | Y | Pass | Pass | Y | Y | N
SES-261023-309 | CTR-342392 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:00 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 530 | Y | Pass | Pass | N | Y | N |  | Upload pending: checksum mismatch, re-upload queued
SES-261023-409 | CTR-292768 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:00 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 150 | Y | Pass | Pass | Y | N
SES-261023-110 | CTR-737494 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:30 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 750 | Y | Pass | Pass | Y | N
SES-261023-210 | CTR-473983 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:30 | Session 1 | ST-2 | Overhead artificial | SUP-C | Lena Okafor | DEV-02 | 550 | Y | Pass | Pass | Y | Y | N
SES-261023-310 | CTR-738444 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:30 | Session 1 | ST-3 | Mixed | SUP-D | Tomas Haddad | DEV-05 | 475 | Y | Pass | Pass | N | N |  |  | Upload pending: checksum mismatch, re-upload queued
SES-261023-410 | CTR-269169 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 14:30 | Session 1 | ST-4 | Warm / low light | SUP-A | Priya Nair | DEV-04 | 115 | Y | Pass | Fail | Y | N |  |  | Retaken on the spot: device task
SES-261023-111 | CTR-119228 | Atlanta, GA | 2026-10-23 | 8 | W4 Fri | 15:00 | Session 1 | ST-1 | Natural (window) | SUP-B | Marcus Bell | DEV-01 | 715 | Y | Pass | Pass | Y | N
SES-261026-101 | CTR-449652 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:00 | Session 1 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-201 | CTR-266976 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:00 | Session 1 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-301 | CTR-587160 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:00 | Session 1 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-401 | CTR-721577 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:00 | Session 1 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-102 | CTR-516156 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:30 | Session 1 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-202 | CTR-970305 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:30 | Session 1 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-302 | CTR-996098 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:30 | Session 1 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-402 | CTR-430508 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 09:30 | Session 1 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-103 | CTR-551137 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:00 | Session 1 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-203 | CTR-507189 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:00 | Session 1 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-303 | CTR-846724 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:00 | Session 1 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-403 | CTR-376597 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:00 | Session 1 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-104 | CTR-986285 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:30 | Session 1 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-204 | CTR-919299 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:30 | Session 1 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-304 | CTR-453453 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:30 | Session 1 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-404 | CTR-146861 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 10:30 | Session 1 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-105 | CTR-591008 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:00 | Session 1 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-205 | CTR-489876 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:00 | Session 1 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-305 | CTR-860735 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:00 | Session 1 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-405 | CTR-627825 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:00 | Session 1 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-106 | CTR-869656 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:30 | Session 1 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-206 | CTR-604606 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:30 | Makeup | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-306 | CTR-154465 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:30 | Session 2 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-406 | CTR-286871 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 11:30 | Session 2 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-107 | CTR-319859 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:00 | Session 2 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-207 | CTR-115285 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:00 | Session 2 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-307 | CTR-273710 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:00 | Session 2 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-407 | CTR-387021 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:00 | Session 2 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-108 | CTR-146409 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:30 | Session 2 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-208 | CTR-182080 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:30 | Session 2 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-308 | CTR-933092 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:30 | Session 2 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-408 | CTR-209045 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 13:30 | Session 2 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-109 | CTR-378503 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:00 | Session 2 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-209 | CTR-970761 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:00 | Session 2 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-309 | CTR-692306 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:00 | Session 2 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-409 | CTR-510440 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:00 | Session 2 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-110 | CTR-558892 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:30 | Session 2 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-210 | CTR-904067 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:30 | Session 2 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-310 | CTR-782499 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:30 | Session 2 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-410 | CTR-203227 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 14:30 | Session 2 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-111 | CTR-546604 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 15:00 | Session 2 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-211 | CTR-608926 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 15:00 | Session 2 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked
SES-261026-311 | CTR-377231 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 15:00 | Session 2 | ST-3 | Mixed | SUP-A | Priya Nair | [9 empty] | Booked
SES-261026-411 | CTR-266255 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 15:00 | Session 2 | ST-4 | Warm / low light | SUP-B | Marcus Bell | [9 empty] | Booked
SES-261026-112 | CTR-380220 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 15:30 | Session 2 | ST-1 | Natural (window) | SUP-C | Lena Okafor | [9 empty] | Booked
SES-261026-212 | CTR-817116 | Atlanta, GA | 2026-10-26 | 9 | W5 Mon | 15:30 | Session 2 | ST-2 | Overhead artificial | SUP-D | Tomas Haddad | [9 empty] | Booked

## Plan
Production day | Date | Day | Planned session 1 | Planned session 2 | Planned makeup | Planned total | Raw capacity | Usable capacity | Planned utilization | Planned validated (cumulative)
1 | 2026-10-12 | W3 Mon | 43 | 0 | 0 | 43 | 48 | 43 | 89.58% | 0
2 | 2026-10-14 | W3 Wed | 28 | 14 | 0 | 42 | 48 | 43 | 87.5% | 0
3 | 2026-10-15 | W3 Thu | 16 | 26 | 0 | 42 | 48 | 43 | 87.5% | 0
4 | 2026-10-16 | W3 Fri | 16 | 26 | 0 | 42 | 48 | 43 | 87.5% | 12
5 | 2026-10-19 | W4 Mon | 21 | 15 | 5 | 41 | 48 | 43 | 85.42% | 35
6 | 2026-10-21 | W4 Wed | 21 | 15 | 3 | 39 | 48 | 43 | 81.25% | 76
7 | 2026-10-22 | W4 Thu | 21 | 20 | 2 | 43 | 48 | 43 | 89.58% | 76
8 | 2026-10-23 | W4 Fri | 21 | 20 | 2 | 43 | 48 | 43 | 89.58% | 92
9 | 2026-10-26 | W5 Mon | 20 | 20 | 3 | 43 | 48 | 43 | 89.58% | 111
10 | 2026-10-28 | W5 Wed | 20 | 19 | 3 | 42 | 48 | 43 | 87.5% | 149
11 | 2026-10-29 | W5 Thu | 21 | 19 | 3 | 43 | 48 | 43 | 89.58% | 149
12 | 2026-10-30 | W5 Fri | 21 | 19 | 3 | 43 | 48 | 43 | 89.58% | 169
13 | 2026-11-02 | W6 Mon | 0 | 39 | 2 | 41 | 48 | 43 | 85.42% | 188
14 | 2026-11-03 | W6 Tue | 0 | 0 | 0 | 0 | 48 | 43 | 0% | 206
15 | 2026-11-04 | W6 Wed | 0 | 0 | 7 | 7 | 48 | 43 | 14.58% | 243
|  | Total | 269 | 252 | 33 | 554 | 720 | 645 | 76.94%
Source: schedule engine, default inputs (deck). Utilization = planned total ÷ raw capacity (4 stations × 12 slots).

## Devices
Device ID | Role | Station | Status | Last pre-flight | Notes
DEV-01 | Active | ST-1 | In service | 2026-10-23
DEV-02 | Active | ST-2 | In service | 2026-10-23
DEV-03 | Active |  | Out of service | 2026-10-21 | Sensor fault W4 Wed 11:30; returned to client for repair
DEV-04 | Active | ST-4 | In service | 2026-10-23
DEV-05 | Hot spare | ST-3 | In service | 2026-10-23 | Swapped into ST-3 on W4 Wed
DEV-06 | Cold spare |  | Standby | 2026-10-19 | Only spare remaining

## Quotas
Dimension | Group | Target recruits
Ancestry group | Asian (East, Southeast, Central) | 102
Ancestry group | Black / African American / Caribbean | 48
Ancestry group | European (Eastern, Western) | 46
Ancestry group | Hispanic / Latino | 38
Ancestry group | Middle Eastern / North African | 35
Gender | Female | 135
Gender | Male | 134
Age band | 18–34 | 94
Age band | 35–54 | 108
Age band | 55+ | 67
Height band | <160 cm | 56
Height band | 160–175 cm | 136
Height band | >175 cm | 77
Targets cover all 269 recruits. Dashboard pace = target × (participants started ÷ recruits planned).

## Settings
Setting | Value
As of | 2026-10-26 08:00
Site | Atlanta, GA
Target Contributions | 250
Recruits planned | 269
Makeup rate plan (%) | 13
Utilization floor (%) | 85
Completed production days | 8